COBWEB project plan

Choosing Occupations: Benchmarking With Electrons and Bosons

QC@B Quantum Computational Chemistry, Fall 2026

Lead: Daniel Boupha Christensen     Advisor: Wendy Billings

Members: Christopher Chen, Tanya Mercado, Alexander Ma, Utsav Lal, Mark Agib, Aodhfionn Bryan Downs

Overview

Selected configuration interaction keeps a subset of a system's configurations instead of all of them, and the answer depends on which ones are kept. We compare two ways of choosing: perturbation theory, and subspace sampling, where the configurations come from measuring a state prepared on a quantum computer. We run both on electronic and vibrational Hamiltonians. The vibrational side is aimed at predicting infrared (IR) spectra and checking them against measured data.

On our model systems the two methods already come out differently for electrons and vibrations. Over the next six weeks we test whether that holds for real molecules.

Deliverables

| Week | Deliverable |
| --- | --- |
| 1 | Selection engine, two model systems, tests, and the first tutorials. |
| 2 | Electronic Hamiltonians for a few small molecules from PySCF, checked against full CI. |
| 3 | Configurations sampled from a real circuit on a simulator, replacing the exact-weight sampler. |
| 4 | Vibrational Hamiltonian for formic acid from ORCA, with its fundamental frequencies compared to NIST. |
| 5 | The comparison on real molecules for both electrons and vibrations, including the frequencies that make up the IR spectrum. |
| 6 | Short report and a results presentation at a general meeting. |

Each week also comes with a short tutorial notebook for the group.

By the end we will have a public repository, a predicted IR spectrum for formic acid next to the measured one, and an answer to whether subspace sampling works as well for vibrations as it does for electrons.

Note: COBWEB has been in progress for a while before this plan. The six weeks above cover the remaining major work, not the full length of the project.